## COMM SERVICES
0
National KPA | KZN PGDS KPA | Outcome 9 | Objectives | Strategy | IDP & SBIP REF No. | Projects | Performance Indicator Ref No. | Unit of Measure / Indicator | Annual Target | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Total | Source of Funding | Ward | POE
[10 empty] | Jul - Sep | Oct - Dec | Jan – Mar | Apr – Jun | Budget for the Year
[10 empty] | Target | Target | Target | Target
IDP AND OPMS SECTION
MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT | Governance and Policy | Improved administrative and human resources management practices | To provide the optimal institutional structure to render effective and efficient services | To manage and enhance the performance of the municipality | MTID-03/16-17 | MID-Year Report | 1 | Council resolution adopting MID-Year report | Council approved MID-Year Report (Section 72) submitted by 25 January 2017 | N/A | N/A | 1 Mid Year Report submitted and adopted by council by 25 January 2017 | N/A | N/A | Operational | N/A | Council Resolution and Mid Year Report
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Cordination | To run the municipality in an open, transparent and accountable manner | To develop a credible IDP as a short- medium term guide for development and service delivery | GGPP-01-16/17 | Integrated Development Plan (IDP)Review | 2 | Council Resolution adopting 2017/18 IDP | Council Approved 2017/18 IDP by 30 June 2017 | Tabling of 2017/18 IDP/Budget/OPMS Process Plan for adoption by council | IDP Ward Consultation meetings, strategic planning Session | Adoption of Draft 2017/18 IDP by council | Adoption of Final 2017/2018 IDP | N/A | Operational | All | Council Resolution approving 2017/2018 IDP and Attendance registers
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Cordination | To run the municipality in an open, transparent and accountable manner | To develop a credible IDP as a short- medium term guide for development and service delivery | GGPP-01-16/17 | Strategic Planning | 3 | Number of strategic planning held | 1 strategic planning held by 31 December 2016 | N/A | Strategic planning Session held | N/A | N/A | N/A | Operational | All | Attendance registers and report
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Cordination | To provide for an effective involvement of the public in municipal affairs | To involve community in shaping the municipality's development agenda | GGPP-03-16/17 | IDP Forum/Stakeholder Engagements (Public sector and private sector) | 4 | Number of IDP Forum/stakeholder engagements held | 4 IDP Forum/ stakeholder engagements held by 30 June 2017 | 1 IDP Forum/ stakeholder engagements held | 1 IDP Forum/ stakeholder engagements held | 1 IDP Forum/ stakeholder engagements held | 1 IDP Forum/ stakeholder engagements held | N/A | Operational | N/A | Attendance registers and minutes
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Cordination | To provide for an effective involvement of the public in municipal affairs | To involve community in shaping the municipality's development agenda | GGPP-03-16/17 | Public Participation | 5 | Number of IDP/Budget, SDF and Precinct Plan public participation | 8 IDP/Budget, SDF and Precinct Plan Public Participation by 30 June 2017 | N/A | 4 IDP/ Budget, SDF and Precinct Plan public participation meetings | N/A | 4 IDP/ Budget, SDF and Precinct Plan public participation meetings | 5000000 | N/A | N/A | Reports with Attendance Registers
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Co-ordination | To provide for an effective involvement of the public in municipal affairs | To involve community in shaping the municipality's development agenda | GGPP-03-16/17 | Public Participation: Annual Report | 6 | Number of Public Participation Meetings on Annual Report | 4 Public Participation Meetings on Annual Report by 31 March 2017 | N/A | N/A | 4 meetings on Annual Report | N/A | 5000000 | N/A | N/A | Reports with Attendance Registers
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Co-ordination | To run the municipality in an open, transparent and accountable manner | To involve community in shaping the municipal development agenda | GGPP-03-16/17 | Oversight Report | 7 | Council Resolution adopting 2015/2016 Oversight report | Council Approved 2015/2016 Oversight Report by 31 March2017 | N/A | N/A | Tabling of oversight report to Council | N/A | N/A | Operational | All | Council Resolution on Adopted, oversight report
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Co-ordination | To run the municipality in an open, transparent and accountable manner | To involve community in shaping the municipal development agenda | GGPP-03-16/17 | Annual Report | 8 | Council Resolution adopting 2015/2016 Annual report | Council Approved 2015/2016 Annual Report by 31 January 2017 | 2015/16 Draft Annual Report tabled to Council by 31 August 2016 | Update of Draft Audited Annual Report | Tabling of Final Annual Report and oversight report to Council | N/A | N/A | Operational | All | Council Resolution on Annual Report Adopted, oversight report and Acknowledgement letter from AG
OFFICE OF THE MUNICIPAL MANAGER
Municipal Transformation and institutional Development | Governance and Policy | Improved administrative and human resources management practices | To provide the optimal institutional structure to render effective and efficient services | To manage and enhance the performance of the municipality | MTID-03-16/17 | Performance Management |  | Number of departmental staff meetings | 12 Departmental meetings by 30 June 2017 | 3 Departmental meetings held | 3 Departmental meetings held | 3 Departmental meetings held | 3 Departmental meetings held | N/A | Operational | N/A | Minutes and attendance registers
Municipal Transformation and institutional Development | Governance and Policy | Improved administrative and human resources management practices | To provide the optimal institutional structure to render effective and efficient services | To manage and enhance the performance of the municipality | MTID-03-16/17 | Performance Management |  | Number of MANCO Meetings held | 12 Departmental meetings by 30 June 2017 | 3 MANCO meetings held | 3 MANCO meetings held | 3 MANCO meetings held | 3 MANCO meetings held | N/A | Operational | N/A | Minutes and attendance registers
Municipal Transformation and Institutional Development | Governance and Policy | Improved administrative and human resources management practice | To provide the optimal institutional structure to render effective and efficient services | To manage and enhance the performance of the municipality |  | Performance Agreements of staff and performance plans |  | Numberof staff performance agreements and work performance plans drafted and signed | 6 staff performance agreements (Risk & Compliance Manager, Internal Audit Manager, IDP/PMS Manager/ Ass IDP/PMS Manager, Special Programms Ass Manager, Planning and Develpopment Manager and Public Realations Officer and 6 work performance plans drafted and signed by 30 June 2017 | 6 of staff performance agreements and 6 work performance plans drafted and signed by staff and supervisors | N/A | N/A | N/A | N/A | Operational | N/A | Performance Agreements and Work Performance Plans
RISK AND COMPLIANCE SECTION
FINANCIAL VIABILITY AND FINANCIAL MANAGEENT | Governance and Policy | To improve finance and administrative capacity | To develop and maintain systems and procedures and sound management of municipal finances | Comply with financial reporting requirement as outlined in the MFMA | GGPP-01-16/17 | Compliance check list | 9 | Number of compliance checklist tabled to COUNCIL for Adoption | 4 Compliance Checklist tabled to Council by 30 June 2017 | 1 Compliance check list tabled to Council | 1 Compliance check list tabled to Council | 1 Compliance check list tabled to Council | 1 Compliance check list tabled to Council | N/A | N/A | N/A | Council Resolutions and compliance checklists
CROSS CUTTING INTERVENTIONS | Governance and Policy | Single Window of Co-ordination | To run the municipality in an open, transparent and accountable manner | To proactively identify and address potential risks that may affect the functioning of the organisation | CCI-03-16/17 | Risk Assessment | 10 | Number Risk asssessment conducted | 1 Risk assessment conducted by 30 September 2016 | Risk assessment Conducted | N/A | N/A | N/A | N/A | Operational | All | Risk Register and attendance register
CROSS CUTTING INTERVENTIONS | Governance and Policy | Single Window of Co-ordination | To run the municipality in an open, transparent and accountable manner | To proactively identify and address potential risks that may affect the functioning of the organisation | CCI-03-16/17 | Risk Register | 11 | Number of updated Risk register prepared | 4- Reports on Updated Risk registers compiled (Organizational and mSCOA) tabled to MANCO by 30 June 2017 | 1 Report o updated Risk Register | 1 Report o updated Risk Register | 1 Report o updated Risk Register | 1 Report o updated Risk Register | N/A | Operational | All | Updated Risk Registers
PUBLIC RELATIONS/COMMUNICATION SECTION
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Co-ordination | To communicate with stakeholders using print and electronic media | To involve community in shaping the municipal development agenda | GGPP-05-16/17 | Newsletters | 12 | Number of newsletters developed and published | 4 newsletters developed and published by 30 June 2017 | 1 Newsletter developed | 1 Newsletter developed | 1 Newsletter developed | 1 Newsletter developed | 850000 | EQS | All | Copy of newsletter (Issue)
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Co-ordination | To communicate with stakeholders using print and electronic media | To involve community in shaping the municipality's development agenda | GGPP-05-16/17 | Radio Slots | 13 | Number of radio slots broadcasted | 4 radio slots broadcasted by 30 June 2017 | 1 Radio slot broadcasted | 1 Radio slot broadcasted | 1 Radio slot broadcasted | 1 Radio slot broadcasted | 1500000 | EQS | N/A | Invoices
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Cordination | To provide for an effective involvement of the public in municipal affairs | To involve community in shaping the municipality's development agenda | GGPP-03-16/17 | Complaints reports | 14 | Council resolution adopting the reviewed customer care policy and Number of complaints reports | Council approved reviewed customer care policy & 4 Reports on Public Complaints registered by 30 June 2017 | 1 Report on Registerd Public Complaints compiled | 1 Report on Registerd Public Complaints compiled | 1 Report on Registerd Public Complaints compiled | 1 Report on Registered Public Complaints Compiled and tabling of reviewed customer care policy to council for approval | N/A | N/A | N/A | Signed Complaints Reports, customer care policy and council resolution
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Cordination | To provide for an effective involvement of the public in municipal affairs | To involve community in shaping the municipality's development agenda | GGPP-03-16/17 | Communication Strategy | 15 | Council Resolution adopting Communications Strategy | Council Approved reviewed communication strategy by 30 June 2017 | N/A | N/A | Tabling of draft reviewed communication strategy to Council | Council Approved Communications Strategy | 1500000 | EQS | N/A | Council resolution on adopted communication strategy
PLANNING AND DEVELOPMENT
CROSS CUTTING INTERVENTIONS | Spatial Equity | Differentiated Approach to Municipal Financing, Planning & Support | To promote productive, hamonious and sustainable land use | To promote development of efficient and sustainable settlement pattern | CCI-01-16/17 | Review Spatial Development Framework (SDF) | 16 | Council Resolution adopting reviewed SDF | Council approved reviewed SDF by 30 June 2017 | Appointment of service provider to review the SDF | Table SDF inception report to council for adoption | Table SDF inception report to council for adoption, Tabling of Draft SDF Review to council for adoption | Tabling of Final SDF Review to council for adoption | 200000 | Operational | All | Council Resolution approved Reviewed SDF, Appointment Letter.
CROSS CUTTING INTERVENTIONS | Spatial Equity | Differentiated Approach to Municipal Financing, Planning & Support | To promote productive, hamonious and sustainable land use | To promote development of efficient and sustainable settlement pattern | CCI-01-16/17 | Strategic Environmental Assessment (SEA) | 17 | Council Resolution adopting SEA | Council approved SEA by 30 June 2017 | Appointment of service provider to develop the Strategic Environmental Assessment (SEA) | Table Strategic Environmental Assessment (SEA) inception report to council for adoption | Table Strategic Environmental Assessment (SEA) inception report to council for adoption, Tabling of Draft Strategic Environmental Assessment (SEA) to council for adoption | Tabling of Final Strategic Environmental Assessment (SEA) to council for adoption | 200000 | Operational | All | Council Resolution approved SEA, Appointment letter
[5 empty] | CCI-01-16/17 | Integrated Transport Plan | 18 | Council Resolution adopting Integrated Transport Plan | Council approved Integrated Transport Plan by 30 June 2017 | Appointment of service provider to develop the Integrated Transport Plan | Table Integrated Transport Plan (inception report) to council for adoption | Table Integrated Transport Plan (inception report) to council for adoptionTabling of Draft Integrated Transport Plan by council for adoption | Tabling of Final Integrated Transport Plan to council for adoption | 200000 | Operational | N/A | Council Resolution approved Integrated Transport Plan and appointment letter
[5 empty] | CCI-01-16/17 | Housing Sector Plan | 19 | Council Resolution adopting Housing Sector Plan | Council approved Housing Sector Plan by 30 June 2017 | Appointment of service provider to develop the Housing Sector Plan | Tabling Housing Sector Plan (inception report) to council for adoption | Tabling Housing Sector Plan (inception report) to council for adoption, Tabling of Draft Housing Sector Plan by council for adoption | Tabling of Final Housing Sector Plan to council for adoption | 200000 | Operational | N/A | Council Resolution approved Housing Plan and appointment letter
[5 empty] | CCI-01-16/17 | Capital Investment Framework | 20 | Council Resolution adopting Capital Investment Framework | Council approved Capital Investment Framework by 30 June 2017 | Appointment of service provider to develop the Capital Investment Framework | Tabling Capital Investment Framework inception report to council for adoption | Tabling Capital Investment Framework inception report to council for adoption, Tabling of Draft Capital Investment Framework to council for adoption | Tabling of Final Capital Investment Framework to council for adoption | 200000 | Operational | N/A | Council Resolution approved Capital Investment Framework and appointment letter
INTERNAL AUDIT
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Improved municipal Finance and Administrative Capability | To comply fully with all minicipal legislation | To enable the organisation to account for the use of public funds | GGPP-05-16/17 | Governance and oversight | 21 | Number of Municipal Public Accounts Committee reports tabled to Council | 4 Municipal Public Accounts Reports Tabled to Council by 30 June 2017 | 1 MPAC report tabled to council for adoption | 1 MPAC report tabled to council for adoption | 1 MPAC report tabled to council for adoption | 1 MPAC report tabled to council for adoption | N/A | Operational | N/A | 4 reports and Council Resolution
| Governance and Policy | Improved municipal Finance and Administrative Capability | To comply fully with all minicipal legislation | To enable the organisation to account for the use of public fund | GGPP-05-16/17 | Governance and oversight (Audit Committee Reports) | 22 | Number of Audit Committee Reports tabled to council | 4 Audit Committee Reports tabled to Council by 30 June 2017 | 1 Audit Committee report tabled to council for adoption | 1 Audit Committee report tabled to council for adoption | 1 Audit Committee report tabled to council for adoption | 1 Audit Committee report tabled to council for adoption | 400000 | Operational | N/A | audit committee reports and council resolution
| Governance and Policy | Improved municipal Finance and Administrative Capability | To comply fully with all minicipal legislation | To enable the organisation to account for the use of public fund | GGPP-05-16/17 | Governance and oversight (Internal Audit Reports) | 23 | Number of Internal audit reports tabled to Audit committee | 4 Internal audit reports tabled to Audit Committee by 30 June 2017 | 1 Internal audit report tabled to Audit committee | 1 Internal audit report tabled to Audit committee | 1 Internal audit report tabled to Audit committee | 1 Internal audit report tabled to Audit committee | 1300000 | Operational | N/A | internal audit reports, AC minutes and attendence register
SPECIAL SOCIAL PROGRAMMES
GOOD GOVERNANCE, PUBLIC PARTICIPATION | Governance and Policy | Single Window of Co-ordination | To provide for an effective involvement of the public in municipal affairs in a structured manner | To provide programmes for designated groups such as youth, women, disabled and other vulnarable groups | GGPP-04-15/16 | Disability Forum and awareness campaigns | 24 | Number of disability forum Reports | 4 meetings on Disabilty Forum and 2 awareness campaigns meetings by 30 June 2017 | 1 disability meeting , submit terms of reference to council for adoption | 1 disability forum meeting and awareness campaign | 2 disability forum meetings and 1 awareness campaign | 1 disability forum meeting | 700000 |  | All | Two reports on awareness campaigns and 4 Disability forum minutes, attendance registers and Council Resolution on TORs
[5 empty] | GGPP-04-15/16 | Women Awareness Campaign and Women Forum Meetings | 25 | Number of Reports on Women Awareness Campaign and Women Forum meetings | 2 women awareness campaigns and 4 women forum meetings held by 30 June 2017 | 1 women awareness campaign Report and 1 women forum meeting and submit terms of reference to council | 1 women awareness campaign Report and 1 women forum meeting | 2 women forum meeting | 1 women forum meeting | 300000 | Operational | All | Attendance Register, 4 Minutes, 2report and council resolution on TORs
[5 empty] | GGPP-04-15/16 | Establish Gender Forum and Gender Awareness Campaigns | 26 | Number of gender forum and reports on gender awareness campaign | Establish 1 Gender Forum and Conduct 2 Gender Awareness Campaign by 30 June 2017 | Establish 1 Gender Forum and submit Terms of reference to council | Gender Forum meeting | Establish Gender Forum, 1 Gender Awareness Campaign and Gender forum meeting | 1 Gender Awareness Campaign and Gender forum meeting | 450000 | Operational | All | Reports on established gender forum, awareness campaigns conducted, minutes, attendance register and council resolution
[5 empty] | GGPP-04-15/16 | Special Programmes (sports codes) | 27 | Number of Reports on Sports programmes ( volleyball, soccer, Athletics and netball codes) | Establishment of 4 Leagues (volleyball, soccer, Athletics and netball codes) by 30 June 2017 | Mayoral Cup Event, Establishment of Asidlale program (leagues), LSC Meetings and AGM | 1 LSC Meeting, Asidlale program and meeting with KZN Athletics and Local Athletes | 2 LSC Meeting and Asidlale progam and meeting with KZN Athletics and Local Athletes | 1 LSC Meeting, Asidlale program and Award Ceremony | 2660000 | Operational | All | Log and fixture, minutes and attendance register of LSC Meetings
[5 empty] | GGPP-04-15/16 | HIV/AIDS and TB Awareness campaigns and LAC meetings | 28 | Number of HIV/AIDS and TB Awareness campaigns and number of LAC reports | 4 HIV/AIDS and TB Awareness campaigns and 4 LAC reports by 30 June 2017 | 1 HIV/AIDS and TB awareness campaign, 1 LAC meeting and Report | 1 HIV/AIDS and TB awareness campaign, 1 LAC meeting and report | 1 HIV/AIDS and TB awareness campaign, 1 LAC meeting and report | 1 HIV/AIDS and TB awareness campaign, 1 LAC meeting and Report | 650000 | Operational | All | Participants attendance register on HIV/AIDS, TB Campaigns, LAC reports and minutes
|  |  | To provide for an effective involvement of the public in municipal affairs | To develop efficient and effective public strusture | GGPP-02-16/19 | Ward Committee meetings and reports | 29 | Number of Ward committee meetings held and reports submitted | 216 ward committee meetings held (18x12) and 12 reports submitted | 54 ward committee meetings and 3 reports | 54 ward committee meetings and 3 reports | 54 ward committee meetings and 3 reports | 54 ward committee meetings and 3 reports | N/A | N/A | N/A | 12 Attendance registers, 12 minutes and 12 reports
[5 empty] | GGPP-04-15/16 | Coaching of artist on 5 genres (Kwaito, HIP HOP, traditional dance, gospel and Maskandi) and moral regeneration (Reed dance) | 30 | Number of Artists coached on music genres (Kwaito, HIP HOP, traditional dance and Maskandi) and number reed dance supported | 2 Reed dance supported (Nongoma and Ingwavuma events) by 30 September 2016, 20 artists coached on 5 genres (Kwaito, HIP HOP, Tradional dance, gospel and Maskandi) by 30 June 2017 | 2 Reed dance events supported, | Music Festival tour and coaching of 10 artist (Kwaito and HIP HOP) | Talent show on 3 genres (Gospel, Traditional dance and Maskandi) | Music Festival tour and coaching of 10 artist (Kwaito and HIP HOP) | 2189417 | Operational | All | Reports on Reed dance and festivals, letter from DaC and participant register
Note on O41: nontos: finance has given us 211 200 isntead of 300 000